COURSE OUTCOME – 1          ASSESSEMENT TOOL - 2

Agile Sprint Planning & User Story Workshop

Smart AI-Based Library Resource Recommendation and Management System

SUBMITTED BY

SANJAY MANESH M

(192511362)

B.E COMPUTER SCIENCE AND ENGINEERING

UNDER THE GUIDANCE OF

Dr LATHA R

# Project Overview

Conventional library management systems focus mainly on catalog management and circulation, offering limited personalization and analytics. This project delivers an AI-powered library platform that automates RFID-based inventory tracking, recommends resources using AI, digitally tracks circulation, predicts demand, manages digital collections, and produces usage analytics — improving both operational efficiency and the member experience.

## Project Objectives

- Automate library inventory management using RFID.

- Recommend books to users through AI-based personalization.

- Track book circulation digitally, end-to-end.

- Predict resource demand ahead of peak periods.

- Manage digital library resources (e-books, journals) centrally.

- Generate actionable library usage analytics.

- Improve the overall user experience and accessibility.

- Enhance library operational efficiency and reduce manual workload.

# 1. Project Vision and Stakeholders

## Project Vision

To transform the library into an intelligent, user-centric knowledge hub — using AI, RFID, and cloud technologies to automate resource management, deliver personalized recommendations, and generate data-driven insights that improve efficiency, accessibility, and member satisfaction.

## Key Stakeholders

| Stakeholder | Interest / Role |
| --- | --- |
| Students / Researchers | Primary borrowers; want fast discovery, personalized recommendations, and digital access. |
| Faculty Members | Use resources for teaching and research; need reserved-reading and bulk-loan support. |
| Public Library Patrons | General public members needing simple search and self-service circulation. |
| Librarians / Circulation Staff | Manage day-to-day check-in/check-out, shelving, and member queries. |
| Acquisition / Collection Development Team | Decide what new titles and licenses to purchase based on demand data. |
| Library Director / Administration | Own budget, policy, and overall service-quality decisions. |
| IT / Database Administrators | Maintain servers, cloud infrastructure, RFID network, and data security. |
| RFID & Hardware Vendors | Supply and maintain RFID tags, readers, and gate sensors. |
| Digital Content Publishers | Provide e-books, journals, and licensing terms for digital collection. |
| Product Owner / Scrum Master / Dev Team | Deliver and maintain the software product through sprints. |

2. Epics and User Stories

The product backlog is organized into eight epics, each mapped to one project objective. Every epic is broken into user stories using the standard format: "As a <user>, I want <feature>, so that <benefit>."

## E1: Automated RFID Inventory Management

Replace manual stock-taking with real-time, RFID-driven inventory tracking.

US-01  As a librarian, I want the system to automatically log book check-in/check-out via RFID scanning, so that I don't have to manually update circulation records.

US-02  As a librarian, I want an alert when a book is detected out of its correct shelf location, so that I can quickly locate and re-shelve misplaced items.

US-03  As a library administrator, I want a real-time inventory count across all branches, so that I can make informed restocking and transfer decisions.

## E2: AI-Powered Book Recommendations

Use borrowing history and content similarity to personalize discovery.

US-04  As a student, I want book recommendations based on my borrowing history and interests, so that I can discover relevant resources faster.

US-05  As a returning user, I want to see "similar books" suggestions on a book's detail page, so that I can explore closely related topics.

US-06  As a new user with no history, I want recommendations based on my department or course of study, so that I still get useful suggestions from day one.

## E3: Digital Circulation Tracking

Digitize the full loan lifecycle from issue to return and fines.

US-07  As a circulation staff member, I want to track book issue and return dates digitally, so that I can manage due dates and fines without paperwork.

US-08  As a borrower, I want an automated reminder before my book's due date, so that I can avoid late fees.

US-09  As a librarian, I want a dashboard listing all currently overdue books, so that I can follow up with borrowers efficiently.

## E4: Resource Demand Prediction

Forecast demand so procurement stays ahead of need.

US-10  As a library administrator, I want a prediction of which titles will be high-demand next semester, so that I can plan procurement in advance.

US-11  As a acquisition officer, I want a forecast of likely shortages during exam periods, so that I can arrange extra copies or digital licenses in time.

## E5: Digital Library Resource Management

Bring e-books, journals, and licenses under one managed system.

US-12  As a student, I want to access e-books and journals directly through the library portal, so that I don't need to visit the physical library.

US-13  As a library administrator, I want to manage digital licenses and access permissions centrally, so that I can ensure compliance with vendor agreements.

US-14  As a user, I want a single search across both physical and digital collections, so that I get complete results in one place.

## E6: Library Usage Analytics

Turn circulation and access data into decision-ready reports.

US-15  As a library administrator, I want a dashboard of monthly circulation trends, so that I can evaluate how well resources are being utilized.

US-16  As a management stakeholder, I want reports on the most and least borrowed categories, so that I can guide budget allocation with evidence.

## E7: Enhanced User Experience

Make discovery and self-service fast and mobile-friendly.

US-17  As a user, I want an intuitive search with filters for author, genre, and availability, so that I can find the right book quickly.

US-18  As a user, I want to reserve a book online when it is currently checked out, so that I'm notified as soon as it becomes available.

US-19  As a mobile user, I want a mobile-friendly interface to browse the catalog and my account, so that I can manage my loans on the go.

## E8: Administrative Efficiency

Automate routine back-office library administration.

US-20  As a librarian, I want the system to automatically calculate and apply late fees, so that I save time on manual billing.

US-21  As a system administrator, I want role-based access control for staff accounts, so that each staff member only sees functions relevant to their role.

# 3. Acceptance Criteria (Given–When–Then)

Acceptance criteria are defined below for the six user stories selected into Sprint 1 (see Section 5).

### US-01: As a librarian, I want the system to automatically log book check-in/check-out via RFID scanning, so that I don't have to manually update circulation records.

Given a book tagged with an RFID chip passes through the library gate/scanner  When it is checked out or checked in by a member  Then the system updates the circulation record and shelf status within 2 seconds without staff intervention

### US-07: As a circulation staff member, I want to track book issue and return dates digitally, so that I can manage due dates and fines without paperwork.

Given a member presents a valid library card and a book at the circulation desk  When the staff member processes an issue or return through the system  Then the loan record, due date, and member's account are updated digitally and a receipt is generated

### US-09: As a librarian, I want a dashboard listing all currently overdue books, so that I can follow up with borrowers efficiently.

Given one or more loans have passed their due date  When a librarian opens the circulation dashboard  Then an "Overdue Books" panel lists borrower name, book title, due date, and days overdue, sorted by longest overdue first

### US-17: As a user, I want an intuitive search with filters for author, genre, and availability, so that I can find the right book quickly.

Given a user is on the catalog search page  When they enter a keyword and apply filters for author, genre, or availability  Then results update within 1 second and only show items matching all selected filters

### US-04: As a student, I want book recommendations based on my borrowing history and interests, so that I can discover relevant resources faster.

Given a logged-in user with at least 3 prior loans visits their home page  When the recommendation widget loads  Then the system displays at least 5 book suggestions ranked by relevance to the user's borrowing history

### US-12: As a student, I want to access e-books and journals directly through the library portal, so that I don't need to visit the physical library.

Given a user searches for a title that has a licensed digital edition  When they click "Read online" or "Download"  Then the e-book or journal opens within the portal respecting the vendor's licensed access limits

# 4. Prioritized Product Backlog

Prioritization uses the MoSCoW technique (Must / Should / Could / Won't-this-time) combined with business value and dependency analysis.

| ID | Epic | Priority | Business Value | Story Pts | Dependencies |
| --- | --- | --- | --- | --- | --- |
| US-01 | E1 | Must | High | 8 | RFID hardware installed |
| US-02 | E1 | Should | Medium | 5 | US-01 |
| US-03 | E1 | Should | Medium | 5 | US-01 |
| US-04 | E2 | Must | High | 8 | US-07 (loan history data) |
| US-05 | E2 | Could | Medium | 3 | US-04 |
| US-06 | E2 | Could | Medium | 5 | US-04 |
| US-07 | E3 | Must | High | 5 | None |
| US-08 | E3 | Should | Medium | 3 | US-07 |
| US-09 | E3 | Must | High | 3 | US-07 |
| US-10 | E4 | Should | High | 8 | US-07, US-15 |
| US-11 | E4 | Could | Medium | 5 | US-10 |
| US-12 | E5 | Must | High | 5 | Vendor licensing agreements |
| US-13 | E5 | Should | Medium | 5 | US-12 |
| US-14 | E5 | Should | High | 8 | US-12 |
| US-15 | E6 | Should | Medium | 3 | US-07 |
| US-16 | E6 | Could | Medium | 3 | US-15 |
| US-17 | E7 | Must | High | 3 | None |
| US-18 | E7 | Should | Medium | 5 | US-07 |
| US-19 | E7 | Could | Medium | 5 | US-17 |
| US-20 | E8 | Should | Medium | 3 | US-07 |
| US-21 | E8 | Must | Medium | 3 | None |

# 5. Sprint Backlog (Sprint 1)

Sprint 1 selects the six highest-priority, foundational "Must Have" stories needed to establish core value: RFID-based circulation, digital loan tracking, an overdue dashboard, searchable catalog, baseline recommendations, and digital resource access.

Sprint duration: 2 weeks  |  Team velocity assumption: ~35 story points  |  Total committed: 32 story points

## US-01 — 8 pts

As a librarian, I want the system to automatically log book check-in/check-out via RFID scanning, so that I don't have to manually update circulation records.

| Task | Owner | Est. Hours |
| --- | --- | --- |
| Configure RFID reader integration at gate & desk | Backend Dev | 8h |
| Build check-in/check-out event listener service | Backend Dev | 6h |
| Update inventory DB schema for RFID tag IDs | Database Dev | 4h |
| Unit + hardware integration testing | QA | 5h |

## US-07 — 5 pts

As a circulation staff member, I want to track book issue and return dates digitally, so that I can manage due dates and fines without paperwork.

| Task | Owner | Est. Hours |
| --- | --- | --- |
| Design loan/return data model (loans, fines, dates) | Backend Dev | 4h |
| Build issue/return API endpoints | Backend Dev | 6h |
| Build circulation desk UI screen | Frontend Dev | 5h |
| Generate digital receipt on transaction | Full-stack Dev | 3h |

## US-09 — 3 pts

As a librarian, I want a dashboard listing all currently overdue books, so that I can follow up with borrowers efficiently.

| Task | Owner | Est. Hours |
| --- | --- | --- |
| Query overdue loans (due date < today) | Backend Dev | 3h |
| Build Overdue Books dashboard panel | Frontend Dev | 4h |
| Add sort by days-overdue | Frontend Dev | 2h |

## US-17 — 3 pts

As a user, I want an intuitive search with filters for author, genre, and availability, so that I can find the right book quickly.

| Task | Owner | Est. Hours |
| --- | --- | --- |
| Index catalog fields for search (title/author/genre) | Backend Dev | 5h |
| Build search bar + filter UI components | Frontend Dev | 5h |
| Wire filters to search API with debounce | Frontend Dev | 3h |

## US-04 — 8 pts

As a student, I want book recommendations based on my borrowing history and interests, so that I can discover relevant resources faster.

| Task | Owner | Est. Hours |
| --- | --- | --- |
| Prepare borrowing-history training dataset | Data/ML Engineer | 6h |
| Train baseline collaborative-filtering model | Data/ML Engineer | 8h |
| Expose recommendation API endpoint | Backend Dev | 4h |
| Build recommendation widget on home page | Frontend Dev | 4h |

## US-12 — 5 pts

As a student, I want to access e-books and journals directly through the library portal, so that I don't need to visit the physical library.

| Task | Owner | Est. Hours |
| --- | --- | --- |
| Integrate e-book/journal viewer (DRM-aware) | Backend Dev | 8h |
| Build "Read online / Download" access flow | Frontend Dev | 5h |
| Enforce vendor license/access limits | Backend Dev | 5h |

# 6. Effort Estimation Using Story Points

Story points were assigned using Planning Poker with the Fibonacci sequence (1, 2, 3, 5, 8, 13), reflecting relative effort, complexity, and uncertainty rather than absolute hours. The full team estimates independently, reveals simultaneously, and discusses outliers until consensus is reached.

| ID | Points | Justification |
| --- | --- | --- |
| US-01 | 8 | Requires RFID hardware integration, event handling, and real-time sync with the inventory database. |
| US-02 | 5 | Needs shelf-location mapping plus RFID signal comparison logic; moderate complexity. |
| US-03 | 5 | Aggregating multi-branch data in real time adds moderate integration effort. |
| US-04 | 8 | Needs a trained recommendation model, ranking logic, and UI integration — high uncertainty. |
| US-05 | 3 | Reuses the same recommendation engine with a narrower, content-similarity scope. |
| US-06 | 5 | Cold-start logic requires a separate rule-based fallback path. |
| US-07 | 5 | Core CRUD workflow but touches loans, fines, and member accounts together. |
| US-08 | 3 | Scheduled notification job; low complexity once circulation data exists. |
| US-09 | 3 | Straightforward filtered/sorted view on existing loan data. |
| US-10 | 8 | Requires historical data analysis and a forecasting model — high uncertainty. |
| US-11 | 5 | Builds on the demand-prediction model with a seasonal (exam period) filter. |
| US-12 | 5 | Needs a digital rights/DRM-aware viewer and license-limit checks. |
| US-13 | 5 | License and permission management with vendor-specific rules. |
| US-14 | 8 | Federated search across two different data sources (physical + digital catalogs). |
| US-15 | 3 | Dashboard on top of already-collected circulation data. |
| US-16 | 3 | Simple aggregation/reporting query with charting. |
| US-17 | 3 | Standard search-with-filters UI on an existing catalog index. |
| US-18 | 5 | Requires queue management and notification triggers when items are returned. |
| US-19 | 5 | Responsive UI rework across existing screens. |
| US-20 | 3 | Rule-based fee calculation on existing due-date data. |
| US-21 | 3 | Standard role/permission matrix, common pattern. |

# 7. Sprint Goal and Expected Deliverables

## Sprint Goal

"Deliver a working core library workflow: members' books are checked in/out automatically via RFID, loans and overdue items are tracked digitally, and members can search the catalog, receive baseline AI recommendations, and access licensed digital resources online."

## Expected Deliverables

- Working RFID check-in/check-out integrated with the inventory database (US-01).

- Digital circulation module recording issues, returns, and due dates (US-07).

- Overdue-books dashboard for library staff (US-09).

- Catalog search with author/genre/availability filters (US-17).

- Baseline AI recommendation widget on the member home page (US-04).

- Online access to licensed e-books/journals through the portal (US-12).

- A sprint demo to the Product Owner and stakeholders, followed by a sprint retrospective.

## Definition of Done

- Code reviewed, merged, and passing automated tests.

- Acceptance criteria for each story verified by QA.

- Feature deployed to the staging environment and demoed.

- Documentation updated for any new API or admin function.